## Tabelle1
Category | Aspect | Evaluation | Time (week) | Note
Category 1: Energy-efficient building refurbishment as a core component of the energy transition | 1.1 Serial renovation | default package | 1 | Serial renovation is added as an option how renovation is done, in comparison with "conventional renovation". They have different cost, as well as the demand of time and craftsman.
Category 1: Energy-efficient building refurbishment as a core component of the energy transition | 1.2 Lower flow and district heating temperature | default package | 3.5 | We can have only demand-side modeling, i.e., low-temperature DH potential is estimated. Grid infrastructure data needs to be developed.
Category 1: Energy-efficient building refurbishment as a core component of the energy transition | 1.3 Refurbishment roadmaps | default package | 1 | Buildings are triggered to be renovated due to minimum efficiency requirement.
Category 1: Energy-efficient building refurbishment as a core component of the energy transition | 1.4 Choice of the optimal energy system | default package | 1 | We have PV (and battery) adoption modeling based on (1) exogenous penetration curve and (2) sync actions with renovation or heating system replacement.
Category 2: Integration of the individual building into the overall system | 2.1 Flexibility potentials on the end consumer side (buildings) | extenstion and budget needed | 4 | We need to export results from RENDER-Building to FLEX for prosumaging modeling (e.g., scenarios of dynamic electricity price and smart meter optimization).
Category 2: Integration of the individual building into the overall system | 2.2 Digitisation pro-gress in the building sector | extenstion and budget needed | 4 | This aspect is modeled together with above.
Category 3: New construction as a driver of innovation | 3.1 Efficiency increase through research work/technology advancement | default package | 0.5 | Higher efficiency requirements are applied to building construction than renovation.
Category 3: New construction as a driver of innovation | 3.2 Mandatory climate-neutral (or plus-energy?) building operation for new buildings | default package | 0.5 | But, "climate-neutral" is simply defined as "PV generation exceeding energy consumption".
Category 3: New construction as a driver of innovation | 3.3 Solar obligation (PV) for new buildings | default package | 0.5 | All new buildings are built with PV panels.
Category 4: Regulatory framework | 4.1 Support programmes | default package | 1.5 | We can model funding demand (given conditions of funding) but not funding limit. Funding limit modeling requires extension and further budget.
Category 4: Regulatory framework | 4.2 Regulatory restrictions for new construction and conversion | default package | 0.5 | Two regulations can be modeled: (1) banning technologies, and (2) 65% RE share.
Category 4: Regulatory framework | 4.3 Redevelopment constraints | default package | 1 | Buildings are triggered to be renovated due to minimum efficiency requirement. This is same with 1.3 but the minimum efficiency requirements can be defined differently.
Category 5: Society and Economy | 5.1 Craft capacities / economic efficiency of the enterprises | default package | 1 | We can model craftsman demand and craftsman limit.
Category 5: Society and Economy | 5.2 Supply chain development | extenstion and budget needed | 8 | We can develop the data of material demand (and limit). We can also include recycling of material from building demolishment.
Category 5: Society and Economy | 5.3 Income development | default package | 0.5 | We can include income group of households as well as the limit in investment decisions. But, we may not be able to link this further to owner/tenant and building type.
Category 5: Society and Economy | 5.4 Household structure and size | default package | 0.5 | But, the living area change is only reflected in new constructions. Because we cannot model people moving across the existing buildings.
| April 8th | May 31st | August 31st
new construction | ref | default package logic | results ready
renovation | ref (without forced renovation) | default package logic | results ready
data development (less logic-intenstive) | not yet | default package logic | results ready
FLEX interaction and material-related calculation (extenstion with further budget) | not yet | not yet | not yet